# CITEMS

# Action plan

# Project DETAILS

| Title: | Copyright and IP Update |
| --- | --- |
| Start Date: | 27/11/2025 |
| End Date: | 4/12/2025 |

| # Action Item | # Planned Completion date | # Status | # Task Completed Date |
| --- | --- | --- | --- |
| Review CITEMS Intellectual Property Policy & compare to current legislation. | 27/11/2025 | Done | 27/11/2025 |
| Discuss findings in Policy Update Meeting | 27/11/2025 | Done | 27/11/2025 |
| Document relevant definitions and research copyright for updating. | 28/11/2025 | Planned |  |
| Amend Policy with findings | 28/11/2025 | Planned |  |
| Update CEO on findings via email | 28/11/2025 | Planned |  |
| Implement CEO feedback | 1/12/2025 | Planned |  |
| Update IT Head via email | 1/12/2025 | Planned |  |
| Once go-ahead is received, send out staff notification email | 2/12/2025 | Planned |  |

APPROVED: Frank Robson

DATE: 27/11/2025